## Sheet1
MANTALONGON NATIONAL HIGH SCHOOL
Mantalongon, Dalaguete, Cebu
ANNUAL IMPROVEMENT PLAN (AIP)
Year 2012
|  |  | TIME FRAME | [11 empty] | Resources Requirements |  | Amount and Sources
Programs/Projects/ | Objectively Verifable Indicators | Means of Verification (MOVs)
Activities | (OVIs |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Person/s | Other | LGU | PTA | DepEd | Others | Total
[15 empty] | Reponsible | Resources
1. Improve physical environment | 4 classroom 2 storey bldg | Lot acquisition on process | [12 empty] | Principal, teachers | DepEd | 100000 |  | 4000000 |  | 4100000 | bar: Jan to Mar; Jun to Sep
for learning (bldg construction) | [14 empty] | parents, students | LGUs
2. Repair of CR (phase 2) | Repaired CR (Male & Female) | Semi completion | [12 empty] | Printipal, teachers | PTA |  | 15000 |  |  | 15000 | bar: Jan to Feb; Jun to Jul; Sep
3. Assessment of existing | Academic classrooms | LGU Engineering Team | [12 empty] | Principal, teachers | LGUs | bar: Jan to Feb
facilities
4. Identify probable donors | Lot acquisation | MNHS PTA and LGU | [12 empty] | Principal, teachers | UYFANG Inc. | bar: Jan to Mar; Jun to Sep
5. PTA Meetings | Lot acquisation | MNHS PTA and LGU | [12 empty] | Principal, teachers | UYFANG Inc. | bar: Jan to Mar; Jun to Sep
6. Attend LGU Sessions | Locally Funded Tearchers | School Hiring Team & LGU | [12 empty] | Principal, teachers | LGU | bar: Apr to Jun
7. Fund Raising Campaign | [14 empty] | Principal, teachers | PTA
8. Procurement of learning materials | MOOE | MOOE Committees | [12 empty] | Principal, teachers | DepEd |  |  | 85000 |  | 85000 | bar: Jan to Mar; Jun to Sep
9. Checking of materials delivered | Learning Materials | BACs Committee | [12 empty] | Principal, teachers | DepEd | bar: Jan to Mar; Jun to Sep
10. Meeting with laborers | CR repair and others | [13 empty] | Principal, teachers | PTA | bar: Jun
11. Supervising and monitoring | Academic dev., Physical MIS | [13 empty] | Principal, teachers | PTA | bar: Jan to Mar; Jun to Sep
12. Repair of physical facilities, | Academic dev., Physical | MOOE Inspection Committee | [12 empty] | Principal, teachers | PTA |  | 43000 | 300500 |  | 343500 | bar: Jan to Mar; Jun to Sep
school furniture and equipment | facilities repair & maintenance
13. Repair of Computers | DICP Implementation | MOOE Inspection Committee | [12 empty] | Principal, ICT | Smart GILAS |  | 25000 | 25000 |  | 50000 | bar: Jun to Sep
14. Solicit funds for lot acquisition | 4 classroom 2 storey bldg | PTA Resolutions | [15 empty] | 143000 |  |  | 143000 | bar: Jan to Mar; Jul to Sep
15. Procurement of Audio Visuals | Academic dev. Physical | ICT Assessment | [12 empty] | Principal, ICT | DepEd |  |  | 40000 |  | 40000 | bar: Jan to Mar; Jun to Sep
equipment and facilities | facilities maintenance | ICT Implementation
16. Tree Planting | Div Memorandum | eGWEN Forms | [12 empty] | Principal, teachers | LGUs | bar: Feb to Mar; Jun to Aug
Prepared by:
RAMON M. CORTES
Principal 1